Idrija, 28.-29. September 2018

**Transnational meeting minutes - Erasmsus+ ROOTS project.**

Participants: José Ángel Molina Carmona, Božena Rudolf, Patrik Roddar, Katerina Christodoulou, Kalliopi Bechraki, Johanna Rasmussen, Stina Lundholm, Belén Alcaraz, José Luis Arbors and Jóhanna Arnórsdóttir.

1.  Revision, evaluation, logistics. Do we need to change anything, improve, any new tasks?

All tasks are on schedule with regard of the project proposal. Division of tasks remains the same according to decisions in the first transnational meeting.

* Sweden is responsible for the homepage. The homepage is up and running as planned. Material to be published on the homepage is saved in a folder on *google drive*.
* Greece is responsible for the facebook page. Coordinators have editing rights on the facebook page and should publish news and photos from local activities.
* Spain is responsible for the baseline and post activities surveys. We have results from the surveys for all activities. There was poor response from teachers after the meeting in Greece. We don´t know why, perhaps people were too busy and did not register that there was one survey for teachers and another for students. They survey will be opened again for a couple of weeks. José Ángel will share the results from the students’ survey (baseline and post-activity).
* Slovenia has been busy preparing the short term teachers training.
* Iceland is responsible for the coordination, meeting minutes and reports as well as for the Wikiloc account. The wikiloc tracks have to be processed for publication. Jóhanna will do that before the next meeting.

2. Interim report

The draft of the interim has already been written. All partners have contributed to the report. Some parts of the report refer to the project as a whole and other to local activities in partner schools.

The draft was reviewed and made ready for submission. We agreed to upload as an annex all the study kits from the learning activities in Greece as well as evidence about the European cultural heritage label and the upgrading of the tracks from Greece to be featured on Google Earth.

Strangely, the partners have different submission deadlines for the interim report. Slovenia already submitted the report some months ago, Iceland and Sweden have their deadline October 1st, whereas Greece and Spain have their deadline in February 2019.

3. Next meetings, dates and plausible programs.

* Sweden next spring semester – students’ exchange/learning activity

Arrival in Stockholm Tuesday 19/3 2019, departure Monday 25/3 2019.

There will be family accommodation the first night. We will visit the school in Lidingö on Wednesday morning and then head for a winter resource in the northern part of Sweden. The bus trip is about 450 km. We will stay four nights in the north and return on Sunday. Then students will stay one night with families and depart on Monday.

* Iceland next fall semester – students’ exchange/learning activity

Arrival Thursday 19/9 2019, departure Wednesday 25/9 2019.

Students will stay with families in the beginning and the end, like in Sweden. We will stay 2-3 nights in Selið, which is a hut in Hveragerði, ca. 50 km east of Reykjavík.

* Spain spring semester 2020 – students’ exchange/learning activity

Arrival 26/3 2020, departure 1/4 2020

An additional transnational meeting on project monitoring will be held in Spain simultaneous to the learning activity.

* Greece

1st week of June.

4. Other

A) Celebration of European day of languages

1-2 teachers from each partner school participated in a panel discussion about cultural heritage.

B) Interview at the local radio station.

Two coordinators were interviewed about the objectives and activities of the project at the radio station in Idrija.