Stockholm, 20. March 2019

**Learning activity - meeting minutes - Erasmsus+ ROOTS project.**

Participants: José Ángel Molina Carmona, Sara Espinar Lamarid, Božena Rudolf, Magdalena Klasinc, Patrik Roddar, Katerina Christodoulou, Maria Panagiotopoulou, Stina Lundholm, Rikard Mettavainio, Arnór Bjarki Svarfdal and Jóhanna Arnórsdóttir.

1. Reception by Caroline Mårtensson vice-principal of Hersby gymnasium

2. Revision of the program of the schedules and learning activities for the coming days, by Patrik Roddar.

3.  Revision, evaluation, logistics of the project. Do we need to change anything, improve, any new tasks?

All tasks are on schedule with regard of the project proposal. Division of tasks remains the same according to decisions at the first transnational meeting.

* Sweden is responsible for the homepage. The homepage is up and running as planned. Material to be published on the homepage is saved in a folder on *google drive*. Photos and news from the international learning and training activities should be published on the homepage.
* Greece is responsible for the facebook page. Coordinators have editing rights on the facebook page and should publish news and photos from local activities as well as from international learning/activities of the project
* Spain is responsible for surveys. There was no baseline query done in this learning activity. There will be a post-evaluation of the meeting in Sweden.
* Iceland is responsible for the coordination, meeting minutes and reports as well as for the Wikiloc account. The wikiloc tracks have to be processed for publication. Jóhanna A. did not have time to do that before this meeting as planned.

Remarks:

* There was an inspection at the Idrija gymnasium, Slovenia. No complaints were made except that the name of the receiving school on the attendance sheet of the kick-off meeting in Iceland was missing.
* José Ángel informs us that a remark was made in another project of his school, about the condition of publishing the Erasmus+ logo and a statement about European support:

*Erasmus+ KA2 – Cooperation for Innovation and the Exchange of Good Practice*

*This publication was supported by the Erasmus+ Programme of the European Commission.*

* There are photos of students both on the project’s homepage and facebook. We stress the importance of having an approval from students/parents to publish these photos. Most schools have done that already in the beginning.

4. Next meetings, dates and plausible programs.

* Iceland next fall semester – students’ exchange/learning activity

Arrival Saturday 21/9 2019, departure Friday 27/9 2019.

Students will stay with families in the beginning and the end, like in Sweden. We will stay 2-3 nights in Selið, which is a hut in Hveragerði, ca. 50 km east of Reykjavík.

José Ángel and Bozena express their interest in sending more students than the 3 that are funded. Also most schools would like to have the possibility to send more than 2 teachers. In total we can expect a group of 16 guest students (max) and 10-15 teachers.

* Spain spring semester 2020 – students’ exchange/learning activity

Arrival 26/3 2020, departure 1/4 2020.

An additional transnational meeting on project monitoring will be held in Spain simultaneous to the learning activity.

*In light of the changes of direct flight (WOW) between Reykjavík and Alicante, the Icelandic partner would ask not to fix these dates until the next meeting in Iceland.*

* Greece

1st week of June – two days transnational meeting. Final dates will be fixed in Reykjavík.